## Timeline_Detail
# | Date | Track | Type | Milestone / Outcome | Primary Artifacts | Status
1 | 2026-04-21 | Setup | Chore | Project initialized and change tracker created | CHANGE_TRACKER.md | Completed
2 | 2026-04-21 | Design | Docs | Architecture review baseline drafted before coding | mock_design/phase1_review_and_architecture.md | Completed
3 | 2026-04-21 | Design | Docs | Phase-wise test and UAT gates added | mock_design/phase1_review_and_architecture.md | Completed
4 | 2026-04-21 | Design Decision | Docs | Workflow/final-owner clarifications captured | mock_design/phase1_review_and_architecture.md | Completed
5 | 2026-04-21 | Design Decision | Docs | Simple Phase 1 defaults locked (overdue/PDF/prompt summary) | mock_design/phase1_review_and_architecture.md | Completed
6 | 2026-04-21 | Design Mockup | Docs | Static multi-page HTML mockup pack created for approval | mock_design/mockup_html_design_v1/* | Completed
7 | 2026-04-23 | Build | Added | Django Phase 0/1 baseline implemented | accounts/*, operations/*, reporting/*, templates/* | Completed
8 | 2026-04-23 | UX | Changed | Shared shell + modern landing/login + richer seed data | templates/base.html, templates/accounts/*, seed_baseline.py | Completed
9 | 2026-04-23 | Fix | Fixed | Root URL loop fixed by moving dashboard route | operations/urls.py | Completed
10 | 2026-04-23 | UX | Changed | Redwood-inspired enterprise visual refinement applied | static/app.css, templates/base.html | Completed
11 | 2026-04-23 | Data + UX | Changed | 50-record seed + pagination across data tables | seed_baseline.py, operations/views.py, reporting/views.py | Completed
12 | 2026-04-23 | UX + Data | Changed | Column filters added to all data tables | templates/operations/*, templates/reporting/reports.html | Completed
13 | 2026-04-23 | Feature | Added | Task logging UI + task details page added | daily_log_form.html, daily_log_detail.html | Completed
14 | 2026-04-23 | Access UX | Changed | Global +Log Task action for allowed roles | templates/base.html | Completed
15 | 2026-04-23 | Feature Governance | Changed | Task edit permissions + JIRA-style update logs | operations/views.py, operations/signals.py | Completed
16 | 2026-04-23 | Docs | Docs | Timeline tracking workbook created and expanded | TimelinesPromptTracking/timeline_tracking.xlsx | Completed
17 | 2026-04-23 | Test | Docs | Phase 1 test execution evidence captured | TimelinesPromptTracking/unit_test_proof_report_2026-04-23.xlsx, TimelinesPromptTracking/phase1_test_results_2026-04-23.txt | Completed
18 | 2026-04-23 | Submission | Docs | Oracle hackathon submission deck prepared | TimelinesPromptTracking/InterMate_Digital_Worker_Submission_FY26_v1.pptx | Completed
19 | 2026-04-24 | API Verification | Test | API-to-UI verification report generated | TimelinesPromptTracking/api_ui_verification_report_2026-04-24.json | Completed
20 | 2026-04-24 | Role Verification | Test | Intern + Mentor GET/PUT verification for Nisarga scenario | TimelinesPromptTracking/role_api_verification_intern_nisarga_2026-04-24.json, TimelinesPromptTracking/role_api_verification_intern_nisarga_2026-04-24.xlsx | Completed
21 | 2026-04-24 | UX Content | Changed | Login demo credentials updated for Nisarga and Gaurav | templates/accounts/login.html | Completed
22 | 2026-04-24 | MCP | Added | InternMate HTTP MCP server implemented with InternMate_* tools | mcp_server/*, internmate/settings.py, requirements.txt | Completed
23 | 2026-04-24 | MCP | Validation | MCP handshake and tools/list validated for Postman flow | mcp_server/server.py, mcp_server/README.md | Completed
24 | 2026-04-24 | Architecture | Docs | MCP auth approach documented for phased hardening | mock_design/phase1_review_and_architecture.md | Completed

## Inputs_And_Agreements
# | Date | Category | What User Suggested / Provided | What Assistant Asked / Clarified | Final Agreement / Outcome
1 | 2026-04-21 | Kickoff | Create directory InternMate | - | Directory created and project initialized
2 | 2026-04-21 | Governance | Track changes and keep change tracker | - | Git initialized + CHANGE_TRACKER maintained
3 | 2026-04-21 | Design Request | Do requirements review first; no code until explicit approval | - | Architecture doc created, code gated by approval
4 | 2026-04-21 | UAT | Add test phase after each build phase | - | Per-phase technical + business UAT gates documented
5 | 2026-04-21 | Workflow | Intern can update workflow state; mentor/manager can always reopen | Explained workflow semantics | Accepted and locked
6 | 2026-04-21 | Ownership | Final Owner should be Independent or Joint only | Explained final owner usage | Accepted and locked
7 | 2026-04-23 | Scope | Multi-project logging Phase 1 = Yes | Asked if allowed in Phase 1 | Accepted and implemented in design baseline
8 | 2026-04-23 | KPI Logic | On Hold = blocked tasks or unresolved dependencies | Asked exact On Hold semantics | Accepted and documented
9 | 2026-04-23 | AI | AI assistance type single-select | Asked single vs multi | Accepted and documented
10 | 2026-04-23 | Visibility | Manager should see all intern progress | Asked role distinction | Accepted and reflected in access design
11 | 2026-04-23 | Visibility | HR summary-only | Asked raw vs summary | Accepted and reflected
12 | 2026-04-23 | Overdue | Keep simple for Phase 1 | Explained overdue logic options | Calendar-day logic selected
13 | 2026-04-23 | Mockup | Show HTML mockups before build | - | Multi-page mockup delivered
14 | 2026-04-23 | Build | Keep initial tech and build | Asked if alternatives desired | Django+DRF+Bootstrap+SQLite used
15 | 2026-04-23 | UX | Common footer/header/menu; modern responsive UI with banners/about | - | Shared shell + landing/login refresh implemented
16 | 2026-04-23 | UX Theme | Upgrade to Oracle Redwood style | - | Redwood-inspired visual pass implemented
17 | 2026-04-23 | Data | Mock records to 50 + pagination | - | 50 seeded + pagination across tables implemented
18 | 2026-04-23 | Data UX | Add filters to every table | - | Filter controls + backend filtering + pagination persistence implemented
19 | 2026-04-23 | Feature Gap | Need Task Details page and task logging UI | - | Task details + create form implemented
20 | 2026-04-23 | Role Access | +Log Task for manager/mentor assigning intern | - | Header action + assignment support enabled
21 | 2026-04-23 | Edit Governance | Need editable form; edit rights owner/manager/assigned intern/admin; JIRA-like intern logs | - | Edit route + strict permissions + change log implemented
22 | 2026-04-23 | Tracking | Create timeline tracking excel | - | Workbook created and now expanded with detailed sheets
23 | 2026-04-24 | Closure | lets works on Phase 1 closure | Confirmed closure checklist and executed tests | Phase 1 closure validation evidence produced
24 | 2026-04-24 | Testing | Create an excel as test cases proof for unit testing | Generated structured workbook with traceability and signoff | Test proof workbook delivered
25 | 2026-04-24 | Submission | Generate PPT in Oracle template with clear messaging | Mapped architecture + implemented features into template | Submission PPT delivered
26 | 2026-04-24 | API Validation | Test all APIs and let UI verify data | Defined verification report approach and executed run | API-to-UI verification report delivered
27 | 2026-04-24 | MCP Request | Build MCP server with InternMate_* naming and HTTP transport | Asked config/auth/runtime clarifications | MCP HTTP server implemented with named tools
28 | 2026-04-24 | MCP Auth | What is auth for MCP? keep info in architecture for later | Clarified current Basic Auth path and future hardening | Documented phased auth plan in architecture doc
29 | 2026-04-24 | Codex Config | Requested exact config.toml format and fixed invalid transport error | Provided corrected transport syntax | Working config pattern confirmed

## Design_Agreements
# | Agreement Area | Agreed Value | Impact on Build
1 | Workflow States | Draft, Submitted, Reviewed, Reopened, Closed; intern can update own state; mentor/manager can always reopen | Workflow actions and permissions matrix in backend/UI
2 | Final Owner | Independent, Joint only | KPI ownership metrics and dropdown constraints
3 | On Hold KPI | Blocked tasks or unresolved dependencies | Dashboard/report logic alignment
4 | AI Assistance Type | Single-select for Phase 1 | Data model + form behavior
5 | Manager Access | Global visibility across all intern progress | Manager view permissions and filtered reporting
6 | HR Access | Summary-only visibility | API/UI redaction policy for task detail text
7 | Overdue Logic | Calendar-day simple logic for Phase 1 | Derived flag and KPI calculations
8 | PDF Export | Minimal summary-first for Phase 1 | Export implementation scope control
9 | Prompt Storage | Summary only; avoid raw prompt storage by default | Responsible AI data handling
10 | Tech Stack | Django + DRF + Bootstrap + SQLite | Implemented baseline architecture
11 | MCP Authentication (Phased) | Dev/local: MCP->API Basic Auth; later production hardening with token/OAuth/JWT and rotation | Allows immediate local integration with planned security uplift

## Phase_Feature_List
Phase | Feature ID | Feature | Detailed Scope | Status | Primary Files
Phase 0 | P0-F01 | Project scaffold | Django project/apps, settings, routing, dependencies, venv baseline | Completed | internmate/*, requirements.txt, manage.py
Phase 0 | P0-F02 | Auth and roles | User profile roles, login/logout, role checks | Completed | accounts/*
Phase 0 | P0-F03 | Master data framework | Master list and items for dropdown configuration | Completed | operations/models.py, seed_baseline.py
Phase 0 | P0-F04 | Common UX shell | Shared responsive header/menu/footer and base template | Completed | templates/base.html, static/app.css
Phase 1 | P1-F01 | Intern/project management model | Intern profiles, projects, assignments with multi-project support | Completed | operations/models.py, seed_baseline.py
Phase 1 | P1-F02 | Daily progress model and workflow | Task fields, workflow states, completion mapping, blockers/dependencies | Completed | operations/models.py, operations/services.py
Phase 1 | P1-F03 | AI usage tracking | Per-task responsible AI capture fields and linked record | Completed | operations/models.py, daily_log_form.html
Phase 1 | P1-F04 | Daily logs UI list | Filterable, paginated table with row actions and status chips | Completed | operations/views.py, templates/operations/daily_logs.html
Phase 1 | P1-F05 | Task create UI | Form for Intern/Mentor/Manager/Admin to log tasks and assign interns | Completed | operations/forms.py, daily_log_form.html
Phase 1 | P1-F06 | Task details UI | Detailed task page with work/AI/dependency/review sections | Completed | daily_log_detail.html, operations/views.py
Phase 1 | P1-F07 | Task edit with permissions | Edit route with owner/assigned-intern/manager/admin permission control | Completed | operations/views.py, operations/urls.py
Phase 1 | P1-F08 | JIRA-style change logs | Field delta + update note capture for intern and task updates | Completed | operations/views.py, operations/signals.py, daily_log_detail.html
Phase 1 | P1-F09 | Dashboard + daily stats | KPI cards and day-wise stats views with filters/pagination | Completed | operations/views.py, dashboard.html, daily_stats.html
Phase 1 | P1-F10 | Reports + exports | Intern summary reports and CSV/XLSX/PDF export | Completed | reporting/views.py, reporting/reports.html
Phase 2 | P2-F01 | Digital guide service abstraction | Pluggable mock/OCI guide provider for task assistance | Pending | Not yet implemented
Phase 3 | P3-F01 | Advanced charting pack | Interactive trend/segment charts for KPI deep-dive | Pending | Not yet implemented
Phase 4 | P4-F01 | Hardening and test coverage | Automated tests, performance/security checks, DB portability closure | Pending | Not yet implemented
Phase 1 | P1-F11 | Role API verification evidence | Intern/Mentor GET/PUT proof artifacts for UAT validation | Completed | TimelinesPromptTracking/role_api_verification_intern_nisarga_2026-04-24.*
Phase 2 | P2-F02 | InternMate MCP HTTP server | HTTP transport MCP service with InternMate_* tools mapped to Django APIs | Completed | mcp_server/server.py, mcp_server/internmate_client.py
Phase 2 | P2-F03 | MCP security hardening | Client-to-MCP auth, tokenized server auth, credential rotation, expanded audit | Pending | Planned

## Effort_Timeline
# | Date | Feature / Capability | Category | Effort (Estimated) | Start-Stop Window | Notes
1 | 2026-04-21 | Repo init + change tracker | Setup | 00:20 | 19:37-19:57 | Initial project bootstrap
2 | 2026-04-21 | Architecture review doc | Design | 01:20 | 19:52-21:12 | Requirements decomposition and technical baseline
3 | 2026-04-21 | Phase UAT gates + clarifications | Design | 01:10 | 21:12-22:22 | Iterative clarification updates and agreement locking
4 | 2026-04-21 | HTML mockup v1 pack | Design | 01:45 | 22:22-00:07 | Multi-page static approval prototype
5 | 2026-04-23 | Django build baseline | Build | 03:10 | 00:35-03:45 | Models, APIs, templates, exports, seed command
6 | 2026-04-23 | Modern UX pass | Build UX | 01:25 | 03:45-05:10 | Shared shell + landing/login modernization
7 | 2026-04-23 | Redwood-inspired UX pass | Build UX | 01:05 | 05:10-06:15 | Palette, hierarchy, components refinement
8 | 2026-04-23 | Mock data to 50 + pagination | Build Data | 00:55 | 06:15-07:10 | Seed expansion and paginated views
9 | 2026-04-23 | Filters across tables | Build Data UX | 01:05 | 07:10-08:15 | Backend filtering + UI controls + persisted pagination
10 | 2026-04-23 | Task details + create form | Build Feature | 01:25 | 08:15-09:40 | UI logging and details flow completion
11 | 2026-04-23 | Task edit + permission matrix + change logs | Build Governance | 01:40 | 09:40-11:20 | Owner/manager/intern/admin rules + audit trail
12 | 2026-04-23 | Timeline workbook creation + expansion | Docs | 00:45 | 11:20-12:05 | Chronology + agreements + phase/features + effort sheets
14 | 2026-04-24 | Phase 1 closure test run + report artifacts | Test/Docs | 00:55 | 11:35-12:30 | Unit tests evidence and closure report updates
15 | 2026-04-24 | Oracle submission PPT preparation | Docs | 00:50 | 12:30-13:20 | Template-aligned narrative and architecture mapping
16 | 2026-04-24 | API-to-UI and role API verification | Test | 01:15 | 13:20-14:35 | Admin/API flow + Nisarga mentor/intern GET/PUT verification
17 | 2026-04-24 | MCP server implementation (HTTP + tools) | Build Integration | 02:05 | 14:35-16:40 | InternMate_* tools, API bridge, docs, settings updates
18 | 2026-04-24 | MCP runtime/debug + Postman handshake validation | Build/Test | 00:50 | 16:40-17:30 | Resolved FastMCP run signature + validated initialize/tools/list
19 | 2026-04-24 | Architecture update for phased MCP auth | Docs | 00:10 | 17:30-17:40 | Added deferred security hardening note
Note | Effort values are estimated active implementation time based on session progression and milestone grouping.

## Summary
Metric | Value
Project | InternMate
Workbook Generated On | 2026-04-24 17:27:25
Total Timeline Milestones | 24
Total User Suggestion/Agreement Items | 29
Total Phase Features Listed | 20
Implemented Features (Completed) | 16
Pending Features | 4
Current State | Phase 0 mostly done, Phase 1 partially done, Phase 2/3/4 pending items remain